## Sheet1
S.No. | Task | Details | Description | Owner(s) | Start Date | End Date | Percentage Complete | Status | Comment
1 | Networking | Design |  | Saransh/Apoorve/Neeraj
Setup(Baadal Setvice/Hosts/Filers/LDAP/Kerberos)
2 | Development | Installation(Baadal Service/Hosts) |  | Shweta/Apoorve
|  | Baadal Service Backend Backbone Structure and Frontend Templates |  | Sonal/Apoorve/Saransh
|  | Baadal Service Frontend (HTML/JAVASCRIPT/VIEWS) |  | Apoorve/Saransh
|  | Baadal Service Backend (Pyhton/Web2py) |  | Sonal/Shweta/Apoorve
--VM Creation
------Normal VM
------Clone VM
------ISO/Qcow image
--VM Operations
------Start
------Suspend
------Resume
------Shutdown gracefully
------Shutdown forefully
------Delete
--VM Admin operations
------Add User to VM
------Accept/Reject User
--Mailing
--Host Finding Algorithms
--Host Performance optimization algorithm
--Migration
--Snapshot
--Wastage check
--Sanity Check
--Task Screen
--VNC Access
--Users and Groups
Monitoring and Failure Recovery System
3 | Database | Designing/Development/Modifications
Event table Triggers
|  | Cron for creating data dump |  | Sonal/Shweta
|  | Migration scripts(migration of data from old app to new app) |  | Sonal/Shweta
4 | Testing | Stress/Load Testing |  | Monika/Jyoti
Unit Testing
Black Box/Flow Testing
White Box Testing
5 | Integration/Performance Analysis | Module Integration
Performance Analysis of the Methods being used
|  | Code Reviews |  | Sorav Sir
6 | Current Baadalcse Bug Fixing |  |  | Apoorve/Saransh
Saransh
Sonal
Shweta
Apoorve
Neeraj
Syam
Atul
Monika
Jyoti